## Quarterly Roadmap
Dell India OOW VA Chat Quarterly Roadmap Overview
Build → Learn → Optimize → Scale ¦ VA chatbot v1 to full-scale, multi-channel, AI-ready support
Quarter | Theme | Focus | Key Goals | Key Milestone | Success Criteria | Key Risks | Status
Q1 | Build | VA chatbot v1 live for B2C | 1. Build and deploy VA chatbot v1 on Salesforce for B2C 2. All L1 automations live — warranty, order tracking, software redirect 3. L2 hardware fault diagnosis decision tree live — top 5 call drivers 4. L3/L4/L5 voluntary connect path with agent SOP active 5. KPI tracking active from day one | VA chatbot v1 live KPI baseline established | 1. VA chatbot v1 live and handling B2C inbound 2. Zero critical decision tree failures in first 30 days 3. Channel adoption baseline captured 4. Agent feedback collected within first 4 weeks | Low B2C adoption — customers default to existing channels Decision tree gaps causing unexpected escalations Service tag validation failures at launch | In Progress
Q2 | Learn | Agent training + B2B onboarding | 1. Train all internal Dell OOW agents on v1 2. Onboard B2B accounts — AM-covered and non-AM — by mid-to-end Q2 3. Collect data from all major checkpoints 4. Identify optimization candidates for Q3 5. Begin Sprinklr technical scoping for WhatsApp bot | 100% agents trained B2B live on VA chat Sprinklr scoping complete | 1. 100% internal agents trained and handling VA chat sessions 2. AM-covered and non-AM B2B accounts live by end of Q2 3. At least 3 decision tree optimization candidates identified 4. Sprinklr scoping document complete | Agent resistance — reverting to handling outside system B2B onboarding slower than expected Sprinklr scoping reveals major architectural differences | Planned
Q3 | Optimize | Decision tree optimization + WhatsApp bot | 1. Iterate on decision trees — fix drop-offs, improve accuracy 2. Add new query types from Q2 findings 3. Act on agent feedback from Q2 4. Build and launch WhatsApp bot on Sprinklr 5. Begin internal agent training for WhatsApp by end of Q3 | FCR improves vs Q1 WhatsApp bot live | 1. FCR rate improves vs Q1 baseline 2. Branch failure rate reduces vs Q1 baseline 3. WhatsApp bot live by end of Q3 4. At least one new query category automated 5. WhatsApp agent training initiated | WhatsApp build on Sprinklr takes longer than expected Optimization introduces new failure points Agent feedback too varied to prioritize | Planned
Q4 | Scale | BPO training + WhatsApp rollout + future-proofing | 1. Train BPO agent partners on VA chat and WhatsApp bot 2. Complete WhatsApp bot rollout and optimization 3. Analyze Q1-Q3 data — remove redundancy, identify automation opportunities 4. Begin scoping LLM/Gen AI transition — planning only, not building 5. Begin strategic reallocation of internal agent capacity toward higher-value work | BPO agents live on both channels LLM/Gen AI scoping complete | 1. BPO agents live on both channels 2. WhatsApp KPIs at parity with VA chat Q2 baseline 3. LLM/Gen AI scoping document signed off 4. Internal agent redeployment plan approved | BPO training quality lower than internal agents Too many parallel workstreams in Q4 LLM migration harder than expected | Planned

## Q1 Sprint Overview
Q1 Sprint Overview for VA Chat v1
6 sprints × 2 weeks ¦ 5 epics ¦ Total: 157 story points ¦ Sprint review = working demo, not a status update
Sprint | Weeks | Theme | Sprint Goal | Epics in Play | Total Points
Sprint 1 | Weeks 1–2 | Foundation | Development environment ready, APIs connected, decision tree fully documented and SME-approved | EPIC-1 | 31
Sprint 2 | Weeks 3–4 | L1 Core Flows | OOH check, main menu, warranty status, and order status flows live in sandbox | EPIC-2 | 32
Sprint 3 | Weeks 5–6 | L1 Complete + L2 Start | Software redirect and closing loop complete. Hardware sub-menu and first 2 fault trees built | EPIC-2 + EPIC-3 | 34
Sprint 4 | Weeks 7–8 | L2 Complete + Handoff | All 5 hardware fault trees complete. Agent handoff (Block 8) built with context-complete transfer | EPIC-3 + EPIC-4 | 34
Sprint 5 | Weeks 9–10 | Integration + QA Begins | OOH handoff, survey trigger, KPI dashboard built. Full L1 + L2 QA begins | EPIC-4 + EPIC-5 | 22
Sprint 6 | Weeks 11–12 | UAT + Go-Live | Agent training complete. UAT passed. VA chat live for B2C with all monitoring active | EPIC-5 | 17
TOTAL | 12 weeks |  |  | 5 epics | 0

## Q1 Epics
Q1 Epics for VA Chat v1
Epic ID | Epic Name | Description | Sprints | Stories | Total Points
EPIC-1 | Foundation & Salesforce Setup | Stand up the development environment, configure the Salesforce bot platform, establish API connections to Dell's service tag, warranty, and order systems, and produce a fully SME-approved decision tree document before any build work begins. | Sprint 1 | 5 | 31
EPIC-2 | L1 Automated Flows | Build all L1 self-service paths: OOH check, main menu, service tag greeting, warranty status, order & dispatch tracking, software redirect to Dell.com, and the closing loop logic with survey trigger. | Sprint 2 + 3 | 6 | 32
EPIC-3 | L2 Hardware Diagnosis Decision Tree | Build the hardware sub-menu and decision tree branches for all 5 fault types (Damage/Liquid, Battery, Display, Keyboard, Performance/Boot), including part-replacement identification and tree-exhaustion escalation to L4. | Sprint 3 + 4 | 5 | 34
EPIC-4 | Agent Handoff, Escalation & Closing Loop | Implement Block 8 agent handoff with context-complete transfer via service tag, OOH handoff message, survey auto-trigger at all session end points, and KPI monitoring dashboard in Salesforce. | Sprint 4 + 5 | 4 | 22
EPIC-5 | QA, UAT & B2C Launch | Full decision tree path QA across all L1 and L2 branches, agent and AM training on VA chat handoff, user acceptance testing with real B2C cases, go-live execution, and monitoring setup from day one. | Sprint 5 + 6 | 4 | 17
TOTAL |  |  |  | 24 | 0

## Q1 Sprint Board
Q1 Sprint Board for VA Chat v1 ¦ 27 Stories, 157 Story Points, 6 Sprints
Story ID | Epic | Priority | Story Title | User Story | Acceptance Criteria | Points | Sprint | Assignee
Sprint 1 · Weeks 1–2 · SPRINT GOAL: Development environment ready, APIs connected, decision tree documented and SME-approved
SF-001 | EPIC-1 | P0 | Salesforce Bot Environment Provisioned and Configured | As a Salesforce developer, I want a properly configured Salesforce sandbox environment so that the development team can begin building VA chat flows without environment blockers. | 1. Sandbox org created and accessible to all 11 core team members with correct role-based permissions. 2. Salesforce Chat / Einstein Bot licence confirmed active and verified in sandbox. 3. Bot basic settings configured — language English, timezone IST, operating hours Mon–Fri 9AM–6PM. 4. Version control connected — Git repo created, branch strategy agreed, all developers confirmed access. 5. Dev, staging, and production environment plan documented and shared with PM. | 5 | Sprint 1 | Salesforce Developer 1
SF-002 | EPIC-1 | P0 | Dell Support API Integration — Service Tag and Warranty | As a VA chat system, I want to query Dell's service tag and warranty APIs so that I can validate a customer's device and return accurate warranty status in real time. | 1. API credentials stored securely in Salesforce Named Credentials — not hardcoded anywhere. 2. Service tag validation returns device model, purchase date, and warranty status correctly. 3. Warranty expiry date and coverage type returned and displayed correctly in sandbox. 4. API error handling implemented — graceful fallback message shown on timeout or failure. 5. Response time under 2 seconds in sandbox. 6. 3-attempt validation logic built — after 3 failed service tag entries, bot offers agent connect. | 8 | Sprint 1 | Salesforce Developer 2
SF-003 | EPIC-1 | P0 | Order and Dispatch Status API Integration | As a VA chat system, I want to query Dell's order management system so that I can return current order and dispatch status to customers asking about their repair or part orders. | 1. Order status API connected and returning live data in sandbox. 2. Fields returned correctly — order number, current status, expected delivery date. 3. Fallback message configured for unavailable, delayed, or error responses. 4. Tested against 5 order states — pending, dispatched, delivered, cancelled, delayed. 5. Response time under 2 seconds in sandbox. | 5 | Sprint 1 | Salesforce Developer 2
SF-004 | EPIC-1 | P0 | Full L1–L5 Decision Tree Documented and SME-Approved | As a QA analyst, I want a fully documented decision tree covering all L1–L5 paths so that every bot flow can be verified against intended logic before build begins. | 1. Decision tree covers all 5 main menu paths — Hardware, Software, Warranty Status, Order Status, Connect to Agent. 2. Hardware sub-menu documents all 5 fault types — Damage/Cracks/Liquid, Battery, Display/Screen, Keyboard/Touchpad, Performance/Boot. 3. All escalation triggers documented — voluntary connect, tree exhaustion, L2→L4, OOH intercept. 4. OOH check logic documented at every relevant decision point. 5. Closing loop logic documented — YES returns to OOH + menu, NO triggers session end and survey. 6. Block 8 handoff logic documented — context transfer, service tag case linkage. 7. Document signed off by both Dell OOW SMEs before sprint ends. 8. Document stored in team repository and shared with all 11 team members. | 8 | Sprint 1 | Business Analyst
SF-005 | EPIC-1 | P0 | Bot Greeting and Service Tag Entry Flow Built | As a customer opening VA chat, I want a clear greeting and a simple way to enter my service tag so that the bot can identify my device and personalise the interaction from the first message. | 1. Greeting message displays clearly with plain-language explanation of what the bot can help with. 2. Service tag input field presented with format guidance. 3. 3-attempt validation active — fails gracefully after 3 attempts with agent connect offer. 4. Valid service tag triggers silent API lookup and proceeds to OOH check. 5. Talk to Agent button visible and functional at session start. 6. Tested on desktop and mobile — layout renders correctly on both. | 5 | Sprint 1 | Salesforce Developer 1
Sprint 2 · Weeks 3–4 · SPRINT GOAL: OOH check, main menu, warranty status, and order status flows live in sandbox
SF-006 | EPIC-2 | P0 | OOH Check Logic Implemented | As a customer contacting Dell outside business hours, I want the bot to acknowledge agent unavailability and offer self-service alternatives so that I am not left waiting for a response that will not come. | 1. OOH check runs at session start and before main menu displays on every session. 2. Within hours (Mon–Fri 9AM–6PM IST): proceeds normally to main menu. 3. OOH state: displays business hours message and Dell.com/support link. 4. OOH menu: Option 5 displayed as currently unavailable. 5. L1 self-service paths remain accessible during OOH. 6. OOH recheck runs on every closing loop YES path before main menu redisplays. | 5 | Sprint 2 | Salesforce Developer 1
SF-007 | EPIC-2 | P0 | Main Menu — 5 Paths Built | As a customer who has validated their service tag, I want a clear main menu so that I can quickly select the type of support I need without confusion. | 1. Five options displayed — 1. Hardware, 2. Software, 3. Warranty Status, 4. Order Status, 5. Connect to Agent. 2. Each option routes to the correct branch — Hardware→Branch A, Software→Branch B, Warranty→Branch C, Order→Branch D, Agent→Block 8. 3. OOH version suppresses Option 5 with unavailability message. 4. Menu re-displays correctly after closing loop YES response. 5. Mobile-responsive layout verified on at least two device sizes. | 3 | Sprint 2 | Salesforce Developer 1 + BA
SF-008 | EPIC-2 | P0 | Branch C — Warranty Status Flow Built and Tested | As a customer checking their warranty status, I want the bot to return accurate warranty information instantly so that I can decide whether to book a repair without speaking to an agent. | 1. Warranty status returned from API — active, expired, or not found. 2. Active: expiry date and coverage type displayed clearly. 3. Expired: OOW status confirmed and repair booking path offered. 4. Not found: graceful fallback with agent connect option. 5. Closing loop triggered after every warranty resolution. 6. Session auto-logged to Salesforce case linked to service tag. | 8 | Sprint 2 | Salesforce Developer 2
SF-009 | EPIC-2 | P0 | Branch D — Order and Dispatch Status Flow Built and Tested | As a customer waiting for a repair part or dispatch, I want the bot to return my current order status instantly so that I do not have to call or email for an update. | 1. Customer prompted to enter order number if not pre-populated. 2. Order status returned — pending, dispatched, delivered, delayed, or cancelled. 3. Expected delivery date displayed where available. 4. Agent connect offered for disputed, missing, or unclear order status. 5. Closing loop triggered after resolution. | 5 | Sprint 2 | Salesforce Developer 2
SF-010 | EPIC-2 | P0 | Salesforce Session Auto-Logging and Service Tag Case Linkage | As an OOW agent receiving a handoff, I want every VA chat session automatically logged in Salesforce and linked to the customer's service tag so that I have full device and interaction history before I open the case. | 1. Every session creates a Salesforce case record automatically on session start. 2. Case linked to customer's service tag — device model, warranty status, purchase date surfaced. 3. Previous VA chat interactions on the same service tag visible within the case. 4. Full conversation transcript stored in case record. 5. Tier classification (L1–L5) logged on case at point of routing. 6. Verified working for both bot-resolved and agent-transferred sessions. | 8 | Sprint 2 | Salesforce Developer 1 + Solution Architect
Sprint 3 · Weeks 5–6 · SPRINT GOAL: Software redirect and closing loop complete. Hardware sub-menu and first 2 fault trees built
SF-011 | EPIC-2 | P1 | Branch B — Software, OS and Drivers Redirect Flow Built | As a customer with a software or OS issue, I want the bot to direct me to the relevant Dell.com self-service resource so that I can resolve common software issues without waiting for an agent. | 1. Software sub-categories offered — OS issues, driver updates, application errors, activation. 2. Each sub-category returns a specific Dell.com support article link. 3. 'Was this helpful?' prompt displayed after redirect. 4. If not helpful: agent connect offered. 5. Closing loop triggered after resolution. | 5 | Sprint 3 | Salesforce Developer 1 + BA
SF-012 | EPIC-2 | P0 | Closing Loop — 'Anything Else?' Logic Finalized Across All L1 Branches | As a customer who has received a resolution, I want the bot to ask if I need further help so that I can address multiple issues in one session without starting over. | 1. Closing loop triggers after every L1 resolution — Branches B, C, and D. 2. YES: OOH recheck runs, then main menu redisplays. 3. NO: farewell message displays, session ends, survey auto-triggers within 60 seconds. 4. Loop tested across all three L1 branches independently. 5. No infinite loop condition possible — session terminates cleanly on NO. | 5 | Sprint 3 | Salesforce Developer 1
SF-013 | EPIC-3 | P0 | Branch A — Hardware Sub-Menu and Fault Tree 1 (Damage/Cracks/Liquid) | As a customer with a hardware damage or liquid issue, I want the bot to walk me through a structured diagnostic so that I can identify my fault type and understand my repair options. | 1. Hardware sub-menu presents all 5 fault types — Damage/Cracks/Liquid, Battery, Display/Screen, Keyboard/Touchpad, Performance/Boot. 2. Fault tree 1 (Damage/Cracks/Liquid) built with 2–3 targeted diagnostic questions. 3. Part replacement identified where applicable — bot names the part clearly. 4. Relevant KB article offered before agent connect. 5. Agent connect offered if KB article not helpful or repair booking needed. 6. Tree exhaustion automatically triggers agent connect. 7. SME 1 sign-off on fault tree accuracy before story is closed. | 8 | Sprint 3 | Salesforce Developer 2 + SME 1
SF-014 | EPIC-3 | P0 | Hardware Fault Tree 2 — Battery | As a customer with a battery issue, I want the bot to diagnose my specific fault and identify whether I need a battery replacement so that I can make a repair decision quickly. | 1. Battery fault tree built with 2–3 diagnostic questions. 2. Distinguishes battery degradation (reduced life) from failure (won't charge/power). 3. Part replacement (battery unit) identified clearly where applicable. 4. KB article offered — battery calibration or settings steps where relevant. 5. Agent connect at tree exhaustion or KB rejection. 6. Same structural logic pattern as fault tree 1 — consistent experience. 7. SME 2 sign-off on fault tree accuracy before story is closed. | 8 | Sprint 3 | Salesforce Developer 2 + SME 2
SF-015 | EPIC-2 | P0 | L1 Integration QA — All Three Branches End-to-End | As a QA analyst, I want to walk every L1 path end-to-end in an integrated test so that no branch leads to a dead end, wrong escalation, or missing message before L2 build begins. | 1. QA matrix created — one row per L1 path (warranty, order, software). 2. Each path tested with valid, invalid, and edge-case inputs. 3. Closing loop tested on every branch — both YES and NO paths. 4. OOH intercept tested at session start and mid-session on all branches. 5. Zero dead-end paths remaining at sign-off. 6. Salesforce case auto-logging verified — session records created and tagged correctly. | 5 | Sprint 3 | QA + BA
Sprint 4 · Weeks 7–8 · SPRINT GOAL: All 5 hardware fault trees complete. Agent handoff built with context-complete transfer
SF-016 | EPIC-3 | P0 | Hardware Fault Trees 3, 4, 5 — Display, Keyboard, Performance/Boot | As a customer with a display, keyboard, or performance issue, I want the bot to run the same structured diagnostic as other fault types so that I receive a consistent, complete hardware support experience. | 1. Three fault trees built — Display/Screen, Keyboard/Touchpad, Performance/Boot. 2. Each tree follows the same 2–3 question logic pattern as fault trees 1 and 2. 3. Part replacement path correctly identified across all three fault types. 4. KB article offered before agent connect on every branch. 5. Tree-exhaustion escalation consistently triggers agent connect across all three. 6. All three trees tested with positive, negative, and edge-case inputs. 7. SME 1 sign-off on accuracy of all three trees before story is closed. | 8 | Sprint 4 | Salesforce Developer 2 + SME 1
SF-017 | EPIC-3 | P0 | L2 to L4 Escalation Trigger and KB Article Offer Logic | As an OOW agent, I want the bot to offer a relevant KB article before escalating to me so that customers with resolvable issues self-serve, and I only receive cases that genuinely need a human. | 1. After hardware fault identified: relevant KB article presented. 2. 'Did this resolve your issue?' prompt displayed after KB article. 3. YES: closing loop triggered — no agent involved. 4. NO or repair needed: agent handoff triggered to Block 8. 5. Tree exhaustion: agent handoff triggered automatically without KB offer. 6. 'Talk to Agent' button visible and active throughout all hardware flows. | 5 | Sprint 4 | Salesforce Developer 1 + BA
SF-018 | EPIC-4 | P0 | Block 8 — Agent Handoff with Context-Complete Transfer | As an OOW agent receiving a chat handoff, I want to see the full conversation history, service tag details, and previous case interactions so that I do not need to ask the customer to repeat themselves. | 1. Agent handoff triggered by — L3/L4/L5 cases, tree exhaustion, voluntary Option 5, KB rejection. 2. Full conversation transcript visible to agent in Salesforce case on accept. 3. Service tag linked — agent sees device model, warranty status, purchase date, and previous OOW cases. 4. Previous VA chat interactions on same service tag surfaced automatically. 5. OOH check at point of agent connect — within hours routes to queue, OOH triggers OOH handoff message. 6. Case tier (L3/L4/L5) pre-populated before agent opens it. | 8 | Sprint 4 | Salesforce Developer 1 + Solution Architect
SF-019 | EPIC-3 | P0 | L2 Hardware QA — All 5 Fault Trees End-to-End | As a QA analyst, I want to walk every hardware decision tree path end-to-end so that no fault branch leads to a dead end, incorrect escalation, or wrong part identification before the L2 build is complete. | 1. QA matrix covers all 5 fault trees — all paths per tree. 2. Positive path (fault identified, part found), negative path (tree exhaustion), and edge cases tested per tree. 3. KB article offer verified on every tree before escalation. 4. Tree-exhaustion escalation verified on every tree. 5. Zero dead-end paths remaining at sign-off. 6. SME 2 reviews QA matrix output and confirms fault logic accuracy. | 5 | Sprint 4 | QA + SME 2
Sprint 5 · Weeks 9–10 · SPRINT GOAL: OOH handoff, survey trigger, KPI dashboard built. Full L1 + L2 QA begins
SF-020 | EPIC-4 | P0 | OOH Handoff Message and Mid-Session Out-of-Hours Handling | As a customer who requests an agent after business hours, I want a clear message explaining unavailability and offering self-service alternatives so that I am not left with an unanswered request. | 1. OOH message displayed — 'Our live support agents are available Mon–Fri 9:00 AM – 6:00 PM IST'. 2. Dell.com/support link provided in OOH message. 3. Session ends cleanly after OOH message — survey auto-triggers. 4. OOH message triggers for mid-session agent requests, not only at session start. 5. No infinite loop — session terminates cleanly after OOH message displays. | 3 | Sprint 5 | Salesforce Developer 1
SF-021 | EPIC-4 | P1 | Survey Auto-Trigger at All Session End Points | As a product manager, I want a satisfaction survey to fire automatically at the end of every session so that CSAT and NPS data is captured from day one without any manual prompting. | 1. Survey triggers after — bot-resolved closing loop NO response, agent-resolved session close, OOH handoff message. 2. Survey collects minimum — overall satisfaction (1–5) and NPS (0–10). 3. Survey response logged to Salesforce and linked to service tag and session record. 4. Survey fires within 60 seconds of session end. 5. Opt-out option available — no forced completion. 6. Data Analyst confirms survey data is populating KPI dashboard correctly. | 5 | Sprint 5 | Salesforce Developer 1 + Data Analyst
SF-022 | EPIC-4 | P0 | KPI Monitoring Dashboard Built in Salesforce | As a product manager, I want a live dashboard in Salesforce showing all four core KPIs from go-live day so that I can monitor platform health without building a separate reporting tool. | 1. Dashboard shows all four KPIs — First Call Resolution Rate, Channel Adoption Rate, Repeat Contact Rate (30-day window via service tag), Intake and Flow Completion Rate. 2. Supporting metrics visible — Premature Escalation Rate, Agent Productivity Rate, Branch Failure Rate. 3. All data auto-populates from case-routing logs — no manual entry required. 4. Dashboard accessible to PM, Data Analyst, Project Manager, and Team Lead. 5. Daily and weekly view available. 6. Data Analyst signs off that all metric definitions match the agreed KPI document. | 8 | Sprint 5 | Salesforce Developer 2 + Data Analyst
SF-023 | EPIC-5 | P0 | Full Decision Tree QA — All L1 and L2 Paths Combined | As a QA analyst, I want to walk every decision tree path end-to-end in a combined integrated test so that no path leads to a dead end, wrong escalation, or missing message before UAT begins. | 1. QA matrix covers all L1 paths and all 5 L2 hardware fault trees. 2. Each path tested with valid, invalid, and edge-case inputs. 3. Closing loop tested on all branches — YES and NO paths. 4. OOH intercept tested at session start, mid-session, and at agent connect request. 5. Block 8 handoff tested — full context transfer verified for each trigger type. 6. Survey trigger verified after each session end type. 7. Zero critical failures remaining at sign-off. Critical failure = any branch terminating without resolution or escalation path. | 8 | Sprint 5 | QA + BA + SME 1
Sprint 6 · Weeks 11–12 · SPRINT GOAL: Agent training complete. UAT passed. VA chat live for B2C with all monitoring active
SF-024 | EPIC-5 | P0 | Agent and AM Training on VA Chat Handoff and Salesforce Case View | As an OOW agent, I want structured training on the VA chat handoff system so that I understand how to handle transferred cases, read the pre-filled context, and escalate correctly from day one. | 1. Training delivered to all OOW agents with minimum 90% attendance. 2. Training covers — how handoffs arrive, reading conversation transcript, service tag case history, L3/L4/L5 SOP. 3. AM training covers — how to track B2B intake request status in Salesforce. 4. Post-training quiz passed by all attendees — minimum 80% score. 5. Quick-reference guide distributed and stored in Salesforce. 6. Training Lead signs off completion before UAT begins. | 5 | Sprint 6 | Training Lead + SME 2
SF-025 | EPIC-5 | P0 | UAT with Real B2C Cases — Go/No-Go Decision | As a product manager, I want to run user acceptance testing with real customer cases before launch so that I am confident the bot handles live inputs correctly and the team is ready to support it. | 1. UAT run with minimum 30 real-case scenarios covering all L1 and L2 paths. 2. Go/no-go criteria defined before UAT begins — maximum 5% path failure rate, zero P0 bugs open. 3. All P0 bugs fixed before go-live authorisation. 4. P1 bugs documented with workaround — deferred to Sprint 7 backlog. 5. Go-live sign-off obtained from PM, Solution Architect, and Dell OOW Lead. 6. Rollback plan documented and confirmed executable before go-live. | 5 | Sprint 6 | QA + PM + Solution Architect + SME 1
SF-026 | EPIC-5 | P0 | VA Chat Go-Live for B2C — Dell India OOW Support | As the Dell India OOW support team, I want the VA chat to go live for B2C customers so that the platform begins delivering measurable value and the KPI baseline is established from day one. | 1. VA chat live on Dell India OOW support channel. 2. All L1 paths active — warranty, order, software redirect. 3. All 5 L2 hardware fault trees active. 4. Block 8 agent handoff operational — all agents confirmed receiving warm transfers. 5. Survey auto-trigger active on all session end points. 6. KPI dashboard showing live data from day one. | 3 | Sprint 6 | PM + Salesforce Developer 1 + Solution Architect
SF-027 | EPIC-5 | P0 | Post-Launch Monitoring — First 48 Hours Incident Response | As a product manager, I want an active incident response plan in place for the first 48 hours post-launch so that any critical failure is caught and resolved before it affects significant customer volume. | 1. On-call PM and Salesforce Developer confirmed available for 48 hours post-launch. 2. Critical failure definition shared with all agents — any branch terminating without resolution or escalation path. 3. Branch failure rate monitored every 4 hours in first 48 hours. 4. Escalation path defined — who gets notified, in what order, for what severity. 5. Rollback trigger criteria defined — if critical failure rate exceeds agreed threshold, rollback executed within 2 hours. 6. Incident log maintained for first 48 hours and shared with full team at 48-hour mark. | 3 | Sprint 6 | PM + Salesforce Developer 1
Q1 TOTAL : 27 stories across 6 sprints | [5 empty] | 157

## Q2 Overview
Q2 Overview ¦ Learn: Internal agent training + B2B onboarding
Theme: Learn ¦ Focus: Internal agent training + B2B onboarding
Quarter Goal
1. Train all internal Dell OOW agents on VA chat v1 — not BPO partners yet. 2. Onboard B2B accounts (AM-covered and non-AM) onto VA chat by mid-to-end Q2. 3. Collect data from all major checkpoints — decision tree drop-offs, query types, agent pain points. 4. Identify at least 3 optimization candidates for Q3 decision tree iteration. 5. Complete Sprinklr technical scoping for WhatsApp bot build in Q3.
Success Criteria
1. 100% internal OOW agents trained and handling VA chat transferred sessions. 2. AM-covered and non-AM B2B accounts both live on VA chat by end of Q2. 3. At least 3 decision tree optimization candidates identified from data. 4. All 6 KPI data points actively tracked and reported weekly. 5. Sprinklr scoping document complete and ready for Q3 build kick-off.
Q2 Epics: High Level Overview
Epic ID | Epic Name | Description | Key Deliverable | Status
EPIC-6 | Internal Agent Training | Design and deliver structured training for all internal Dell OOW agents on the VA chat handoff system, Salesforce case view, transferred session handling, and L3/L4/L5 SOP. Includes post-training assessment and quick-reference guide. | 100% agents trained, quiz passed, guide distributed | Planned
EPIC-7 | B2B Onboarding — AM-Covered and Non-AM Accounts | Onboard enterprise B2B accounts onto VA chat structured intake. Two distinct onboarding paths: AM-covered accounts (leverage AM relationships for introductions) and non-AM mid-market accounts (direct outreach, given no AM relationship exists). Target: live by mid-Q2. | Both B2B segments live on VA chat by week 6 of Q2 | Planned
EPIC-8 | Data Collection and Optimization Analysis | Actively track all 6 defined data points — branch failure rate, manually handled query types, premature escalation rate, channel adoption split, parts replacement conversion rate, post-session CSAT. Compare against Q1 baseline and produce optimization candidates report for Q3. | Optimization candidates report delivered, Q2 vs Q1 baseline comparison complete | Planned
EPIC-9 | Sprinklr Technical Scoping for WhatsApp Bot | Assess Sprinklr's WhatsApp API capabilities and architectural requirements for replicating the VA chat decision tree on the WhatsApp channel. Identify integration complexity, timeline risk, and any structural differences from the Salesforce-native build. Output: scoping document signed off before Q3 begins. | Sprinklr scoping document complete and signed off | Planned
Sprint-level detail for Q2 will be planned at the start of Q2 based on the previous quarter's retrospective data.

## Q3 Overview
Q3 Overview ¦ Optimize: Decision tree optimization + WhatsApp bot
Theme: Optimize ¦ Focus: Decision tree optimization + WhatsApp bot
Quarter Goal
1. Iterate on decision trees — fix drop-offs identified in Q2, optimize branches, improve accuracy. 2. Automate at least one new query type identified from Q2 agent feedback and data. 3. Act on agent feedback collected in Q2 — UX fixes and tree fixes prioritized by branch failure data. 4. Build and launch WhatsApp bot on Sprinklr using optimized Q2/Q3 decision trees. 5. Begin internal agent training for WhatsApp channel by end of Q3.
Success Criteria
1. FCR rate measurably improves vs Q1 baseline. 2. Branch failure rate reduces vs Q1 baseline. 3. WhatsApp bot live on Sprinklr by end of Q3. 4. At least one new query category automated from Q2 findings. 5. WhatsApp agent training initiated before end of Q3.
Q3 Epics: High Level Overview
Epic ID | Epic Name | Description | Key Deliverable | Status
EPIC-10 | Decision Tree Optimization | Using Q2 branch failure data, premature escalation data, and agent feedback as the objective filter, identify and fix the highest-impact decision tree failure points. Every modified branch re-tested in staging before deploying live. Branch failure rate monitored weekly post-deployment. | FCR and branch failure rate both improve vs Q1 baseline | Planned
EPIC-11 | New Query Type Automation | Automate at least one net-new query category surfaced from Q2's 'query types handled manually by agents' data point. New tree built, QA'd, and deployed using the same decision tree methodology established in Q1. | At least one new query category live and auto-resolving | Planned
EPIC-12 | WhatsApp Bot Build on Sprinklr | Build the WhatsApp bot on Sprinklr using the optimized decision trees from Q3 Epic-10. Scoping completed in Q2 means build can begin immediately in Q3. Includes QA across all paths before launch and a staged rollout to limit exposure if issues arise. | WhatsApp bot live on Sprinklr by end of Q3 | Planned
EPIC-13 | WhatsApp Agent Training | Design and begin delivery of agent training for the WhatsApp channel. Builds on the VA chat training from Q2 — agents already understand the handoff model; Q3 training focuses on WhatsApp-specific differences in session handling and Sprinklr interface. | WhatsApp agent training initiated — full completion in Q4 | Planned
Sprint-level detail for Q3 will be planned at the start of Q3 based on the previous quarter's retrospective data.

## Q4 Overview
Q4 Overview ¦ Scale: BPO training + WhatsApp rollout + future-proofing
Theme: Scale ¦ Focus: BPO training + WhatsApp rollout + future-proofing
Quarter Goal
1. Train BPO agent partners on both VA chat and WhatsApp bot — led by senior internal agents who have run both channels since Q1/Q3. 2. Complete WhatsApp bot rollout, optimization, and stabilization. 3. Analyze Q1–Q3 data comprehensively — remove redundancy, identify further automation opportunities. 4. Begin scoping LLM/Gen AI transition — planning and evaluation only, no build commitment in Q4. Trigger: Q3 FCR plateau confirming rule-based optimization is exhausted. 5. Begin strategic reallocation of internal agent capacity from transactional queues toward higher-value commercial accounts.
Success Criteria
1. BPO agents live and independently handling both VA chat and WhatsApp transferred sessions. 2. WhatsApp KPIs tracking at parity with VA chat Q2 baseline. 3. Q1–Q3 comprehensive data analysis report produced and shared with stakeholders. 4. LLM/Gen AI scoping document signed off — build vs buy decision framed, not made. 5. Internal agent redeployment plan approved by PM and stakeholders.
Q4 Epics — High Level Overview
Epic ID | Epic Name | Description | Key Deliverable | Status
EPIC-14 | BPO Agent Training | Train external BPO agent partners on both channels — VA chat and WhatsApp. Training led by senior internal agents who have run the platform since Q1, giving BPO agents access to real operational knowledge, not just documentation. Sequenced: WhatsApp optimization first half of Q4, BPO training second half. | BPO agents live on both channels, independently handling transferred sessions | Planned
EPIC-15 | WhatsApp Optimization and Stabilization | Complete WhatsApp rollout and run the same optimization cycle applied to VA chat in Q3 — identify branch failures, fix drop-offs, and confirm KPIs are tracking at parity with the VA chat Q2 baseline. Unified dashboard active showing both channels side by side. | WhatsApp KPIs at parity with VA chat Q2 baseline; unified dashboard live | Planned
EPIC-16 | Q1–Q3 Comprehensive Data Analysis Report | Produce a full cross-quarter analysis of all 6 tracked data points across Q1, Q2, and Q3. Identify patterns, redundancies, and remaining automation opportunities. Output feeds directly into the LLM/Gen AI scoping document and the internal agent redeployment plan. | Q1–Q3 data report complete and signed off by PM and Data Analyst | Planned
EPIC-17 | LLM / Gen AI Scoping | Scope the transition from rule-based decision engine to LLM-powered automation. Triggered when Q3 data confirms FCR has plateaued — confirming rule-based optimization is exhausted and AI is the next lever. Output: technical requirements, vendor evaluation, build vs buy recommendation. No build commitment in Q4. | LLM/Gen AI scoping document signed off by stakeholders | Planned
EPIC-18 | Internal Agent Redeployment Plan | As VA chat absorbs L1/L2 volume, systematically redeploy internal agents previously assigned to transactional queues toward higher-value commercial account work and L3/L4/L5 cases. Plan produced by Training Lead and Project Manager in Q3, approved and executed through Q4. | Agent redeployment plan approved; reallocation underway by end of Q4 | Planned
Sprint-level detail for Q4 will be planned at the start of Q4 based on the previous quarter's retrospective data.